## Sheet1
Sr No	Task	Task Details	Assigned by	Assigned Date	Completion Status	Completion Date	Describe the work done
1	class diagram of	created class diagram	snehal	20.9.11	completed	20.9.11	created the over all class diagram of dash go application
	dash go.

2	dash go walk through		snehal	20.9.11	completed	20.9.11	understand the project and gone through ,few important features of it.

3	Model class diagram of	created model class diagram snehal		21.9.11	not completed		created the over all model class diagram of dash go application but needs little modification
	dash go.

4	Model class diagram of	created model class diagram snehal		21.9.11	completed	22.9.11	created the over all model class diagram of dash go application .
	dash go.

5	documentation of	will make a document	snehal	22.9.11	not completed		has started with application controller and will continue
	class methods	explaining the method					with other controller.
		functionality

6	solved an issue	created a migration	snehal	23.9.11	completed	23.9.11	there are some fields in trackers form,not takins decimal values
	for tracker	file for changes in database	and mukul				as input,so changes are made to solve that issue
	and commited

7	documentation of	To create a documentation	snehal	23.9.11	not completed		documentation for three controllers are done
	controllers of	for each controller class
	dashgo

8	documentation of admin	To create a documentation	snehal	24.9.11	40 methods		there are approx 100 methods in this controller out of which
	controllers of	for admin controller class			completed		documentation of 40 methods are done.
	dashgo

9	documentation of admin	To create a documentation	snehal	24.9.11	72 methods		now documentation of 72 methods are done.
	controllers of	for admin controller class			completed
	dashgo

10	documentation of admin	To create a documentation	snehal	24.9.11	completed		all methods done but need to write the output of all queries by
	controllers of	for admin controller class					executing all of them.
	dashgo

11	documentation of admin	To create a documentation	snehal	24.9.11	2 controller		documentation and query explanation of
	controllers of	for admin controller class			completed		two controllers done
	dashgo	and other controllers

12	documentation of	To create a documentation	snehal	24.9.11	3 controller
	controllers of	all			completed
	dashgo	other controllers